8/26/04

### Friends of the Bracewell Observatory

#### Draft Project Timeline and Expense Forecast

## Project Timeline

| Milestone |  | Q3/Q4 ‘04 | Q1 ‘05 | Q2 ‘05 | Q3 ‘05 | Q4 ‘05 |
| --- | --- | --- | --- | --- | --- | --- |
| Establish 501(c)(3), board & officers |  | XXX |  |  |  |  |
| Form core restoration volunteer team |  | XXX |  |  |  |  |
| Volunteer recruitment |  | XXX | XXX | XXX | XXX | XXX |
| Initial site cleanup and painting |  | XXX | XXX | XXX |  |  |
| Initial fundraising drive |  | XXX | XXX | XXX |  |  |
| Site caretaker |  |  |  |  | XXX | XXX |
| Restoration of 1st dish |  |  |  |  | XXX | XXX |
| Restoration of building facility |  |  |  |  | XXX | XXX |
| Begin observational programs |  |  |  |  |  | XXX |

## Expense Forecast for Year 1

## (Note: For Woodbury/GATech dual 100 foot abandoned AT&T dish site: annual cost was $57K/yr with paid caretaker)

| Expense |  | Q3/Q4 ‘04 | Q1 ‘05 | Q2 ‘05 | Q3 ‘05 | Q4 ‘05 |
| --- | --- | --- | --- | --- | --- | --- |
| Formation of 501(c)(3) |  | $300* |  |  |  |  |
| Equipment, materials, and paint for volunteer cleanup |  | $500* | $500* | $500* |  |  |
| Volunteer recruitment* |  | 0* | 0* | 0* | 0* | 0* |
| Project Website, Listserver* |  | 0* | 0* | 0* | 0* | 0* |
| Site caretaker ($30K/yr if paid or zero if volunteer) |  |  |  |  | $7.5K or Zero | $7.5K or Zero |
| Utilities |  | $300* | $300* | $300* | $1200 | $1200 |
| Phone / Connectivity |  |  |  |  | $300 | $300 |
| Liability Insurance |  |  |  |  | $500 | $500 |
| Restoration of 1st dish |  |  |  |  | $6000 | $5000 |
| Restoration of building facility |  |  |  |  | $12000 | $0 |
| Begin observational programs |  |  |  |  |  | $5000 |
| QUARTERLY TOTALS: |  | $1,100* | $800* | $800* | $27,500 | $19,500** |

* Provided by contributions by individual members of SARA, SAS, and the core volunteer team

**Annualizes to $78K/year (or $48K/year if volunteer caretaker).  Total cost through Q4 ’05: $50K